## Ibanda DLG 2020-21 Proc plan
PROCUREMENT PLAN FOR GOODS, WORKS AND NON-CONSULTANCY SERVICES
| Name of Procuring Entity: |  | IBANDA DISTRICT LOCAL GOVERNMENT
| Financial Year: | 2020/2021
S/No. | Subject of Procurement |  | Plan vs. Actual | [6 empty] | Invitation for Bids and Evaluation |  |  |  |  | Contract Finalization
[10 empty] | Invitation for Bidding |  | Bid Evaluation and Contract Award
|  | DEPARTMENT |  | Estimated Cost (UGX) | Source of Funding | procurement type | procurement method | contract type | prequalification ( yes/ No) | Bid Invitation Date | Bid Closing-Opening | Submission Bid Evaluation Report | Approval by CC | Award Notification Date | Contract Signature Date | Completion Date
1 | supply of fuel and lubricants for mechanised road maintenance | works | Plan | 93,967,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
2 | supply of assorted stationery | works | Plan | 5,155,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
3 | supply and installation of culverts | works | Plan | 16,000,000= | GOU | WORKS | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
4 | supply of gravel | works | Plan | 10,765,000= | GOU | SUPPLIES | DIRECT PROC'T | lumpsum | no | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
5 | supply of computer and ICT supplies | works | Plan | 3,600,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
6 | supply of tyres | works | Plan | 32,713,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
7 | supply of road workers' safety ware | works | Plan | 3,186,000= | GOU | SUPPLIES | DIRECT PROC'T | lumpsum | no | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-30
Actual
8 | Building and compound maintenace | works | Plan | 8,700,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
9 | Maintenance of vehicles | works | plan | 15,900,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
10 | supply and installation of solar powererd lighting system for Kashozi water system | Water | Plan | 10,000,000= | GOU | WORKS | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
11 | supply of construction materials for Kibanda GFS and Kogabe GFS | Water | plan | 48,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
12 | construction of a 4 stance latrine with a urinal in Ishongororo S/County | Water | plan | 46,000,000= | GOU | WORKS | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
13 | supply of fuel and lubricants | Water | plan | 8,600,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
14 | supply of stationery | water | plan | 4,800,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
15 | supply of tyres and vehicle servicing | Water | plan | 3,300,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
16 | supply of pipes and fittings for construction of Kogabe GFS in kicuzi | Water | plan | 190,000,000= | GOU | WORKS | OPEN BIDDING | lumpsum | YES | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Atual
17 | construction of piped water system phase 1 in Kijongo sub county | water | plan | 120,800,000= | GOU | WORKS | OPEN BIDDING | admeasurement | YES | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
18 | construction of walkways at ishongororo health centre IV and stone pitching | Health | plan | 31,000,000= | GOU | WORKS | SELECTIVE BIDDING | admeasurement | No | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
19 | supply of fuel and lubrica nts | Health | plan | 15,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
20 | supply of assorted stationery and office equipment | Health | Plan | 3,370,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
21 | upgrading of Kihani Health centre II to health centre III | Health | Plan | 650,000,000= | GOU | Works | OPEN BIDDING | admeasurement | Yes | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
22 | supply of Medical equipment for Kihani health centre II | Health | plan | 198,937,500= | GOU | SUPPLIES | OPEN BIDDING | lumpsum |  | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
23 | Rennovation of Kijongo HCII | Health | plan | 12,956,190= | GOU | WORKS | sELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
24 | construction of 2 stance pit latrine at Kanywambogo Health Centre III | Health | plan | 15,000,000= | GOU | WORKS | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
25 | repair and servicing of motorvehiles | Health | Plan | 6,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
26 | construction of a 2 classroom block with an office at Kanoni ii Primary School in Rukiiri S/C | Education | Plan | 82,000,000= | GOU | WORKS | OPEN BIDDING | admeasurement | no | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
27 | construction of a 2 classroom block with an office at Rwemirama Primary school in Nyamarebe S/C | Education | plan | 82,000,000= | GOU | WORKS | OPEN BIDDING | admeasurement | no | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
28 | construction of a 2 classroom block with an office at Kihani COU P/S | Education | plan | 82,000,000= | GOU | WORKS | OPEN BIDDING | admeasurement | no | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
29 | printing and supply of Mock and P 6 End of year exams | Education | Plan | 10,000,000= | GOU | SUPPLIES | OPEN BIDDING | lumpsum | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
30 | supply of fuel and lubricants | Education | Plan | 30,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
31 | supply of assorted stationery | Education | Plan | 5,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
32 | motorvehicle repairs and tyres | Education | plan | 9,400,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
33 | supply of science and chemical reagents kits for Rwenshambya seed school | Education | plan | 56,000,000= | GOU | SUPPLIES | OPEN BIDDING | lumpsum | no | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
34 | supply of ICT ( computers) and their accessories for the ICT Lab at Rwenshambya seed school | Education | plan | 154,475,000= | GOU | SUPPLIES | OPEN BIDDING | lumpsum | no | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
35 | supply of fuel and lubricants | Finance | plan | 6,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
36 | supply of assorted and printed stationery and small office equipment | Finance | Plan | 16,800,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
37 | computer servicing and engravement | Finance | Plan | 1,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
38 | Rennovation of the administration block | Finance | Plan | 35,000,000= | GOU | Works | SELECTIVE BIDDING | Admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
39 | supply of meals and refreshments | Finance | Plan | 2,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
40 | purchase of airtime | Finance | plan | 2,000,000= | GOU | SUPPLIES | MICRO PROC'T | lumpsum
Actual
41 | supply of irrigation kits | Production | Plan | 41,000,000= | GOU | SUPPLIES | OPEN BIDDING | lumpsum |  | 2020-08-12 | 2020-09-01 | 2020-09-04 | 2020-09-08 | 2020-09-21 | 2020-09-25 | 2021-03-30
Actual
42 | supply of fuel and lubricants | Production | Plan | 97,348,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
43 | supply of assorted stationery,and photocopying services | Production | Plan | 1,759,724= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
44 | supply of a laptop computer | Production | Plan | 3,000,000= | GOU | SUPPLIES | sELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
45 | Maintenance and repair of motor cycles | CBS | Plan | 2,400,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
46 | supply of office shelves,carpets and cupboards | CBS | Plan | 400,000= | GOU | SUPPLIES | MICRO PROC'T | lumpsum | NO | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-30
Actual
47 | supply of computer and ICT accessories | CBS | Plan | 6,000,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
48 | supply of meals and refreshments | CBS | Plan | 3,600,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual | bar: 2020-06-30 to 2020-07-25
49 | supply of a water dispenser, mineral water and disposables | CBS | Plan | 1,450,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
50 | supply of office stationery, cleaning materials and other small office equipment | CBS | plan | 2,450,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | YES | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
51 | Supply of fuel | CBS | plan | 4,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
52 | supply of assistive devices for PWDS | CBS | plan | 600,000= | GOU | SUPPLIES | DIRECT PROC'T | Lumpsum | no | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-30
Actual
53 | supply o office stationery | INTERNAL AUDIT | Plan | 600,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
54 | supply of fuel and lubricants | INTERNAL AUDIT | Plan | 3,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
55 | supply of corporate wear | INTERNAL AUDIT | Plan | 200,000= | GOU | SUPPLIES | MICRO PROC'T | lumpsum | no | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-30
actual
56 | supply of assorted stationery | PROCUREMENT | Plan | 2,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
57 | supply of fuel | NATURAL RESOURCES | Plan | 800,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
58 | supply of assorted stationery | NATURAL RESOURCES | Plan | 1,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
59 | computer Maintenance | NATURAL RESOURCES | Plan | 1,000,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
60 | supply of office stationery | PLANNING UNIT | Plan | 4,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
61 | supply of fuel | PLANNING UNIT | Plan | 6,000,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
62 | repair and maintenance of computer | PLANNING UNIT | Plan | 500,000= | GOU | SERVICES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
63 |  | PLANNING UNIT | Plan | 3,378,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
Actual
64 | Renovation of the slaughter abbattoir at Nyantsimbo in Ishongororo Town council | Ishongororo TC | Plan | 20,000,000= | GOU | Works | SELECTIVE BIDDING | Admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
65 | Supply and installation of Culverts | ISHONGORORO T/C | Plan | 16,000,000= | GOU | Works | SELECTIVE BIDDING | lumpsum | YES | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
66 | Installation of solar powered street lights | ISHONGORORO T/C | plan | 12,000,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | YES | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
67 | Supply and installation of Culverts | RWENKOBWA TOWN COUNCIL | plan | 14,600,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
68 | construction of a slaughter slab phase 1 | RWENKOBWA TOWN COUNCIL | Plan | 5,400,000= | GOU | Works | sELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
69 | Suppl of stationery | RWENKOBWA TOWN COUNCIL | Plan | 2,500,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
actual
70 | Supply of twin desks for schools | Nyamarebe sub county | Plan | 16,000,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
71 | supply of tjree seater twin desks to Kicuzi Subcounty | KICUZI SUB COUNTY | Plan | 7,900,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
actual
72 | construction of a 2 stance pit latrine at Muziza P/S in Ishongororo Sub county | ISHONGORORO SUB-COUNTY | Plan | 12,00,000= | GOU | Works | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
73 | Renovation of office Building | KEIHANGARA SUB-COUNTY | Plan | 7,500,000= | GOU | Works | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
74 | Construction of a 2 stance pit latrine at Kihani Health centre II | KIKYENKYE SUB-COUNTY | Plan | 8,000,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
75 | construction of a 2 stance pit latrine at Rrwatibare P/S | KIJONGO SUB-COUNTY | Plan | 7,600,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
Actual
76 | Fuel, oil and Lubricants | IGORORO TOWN COUNCIL | Plan | 24,228,160= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
actual
77 | Supply and installation of Culverts | IGORORO TOWN COUNCIL | Plan | 8,540,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
78 | Supply of stationery both assorted and printed | IGORORO TOWN COUNCIL | Plan | 3,300,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
actual
79 | Installation of solar powered street lights | IGORORO TOWN COUNCIL | Plan | 11,250,000= | GOU | Works | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
80 | Supply of cutting edges | IGORORO TOWN COUNCIL | Plan | 4,884,000= | GOU | SUPPLIES | OPEN BIDDING | Framework | Yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
actual
81 | Supply of computer laptop and ICT supplies | IGORORO TOWN COUNCIL | Plan | 4,600,000= | GOU | SUPPLIES | SELECTIVE BIDDING | lumpsum | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
82 | Supply of Tree seedlings | IGORORO TOWN COUNCIL | Plan | 220,000= | GOU | SUPPLIES | DIRECT PROC'T | lumpsum | NO | N/A | N/A | N/A | N/A | N/A | N/A | 2021-06-30
actual
83 | supply of three seater twin desks to Nyabuhikye Subcounty | Nyabuhikye sub county | plan | 6,000,000= | GOU | Works | OPEN BIDDING | Framework | yes | 08-06-020 | 2020-06-30 | 2020-07-03 | 2020-07-07 | 2020-07-21 | 2020-07-25 | 2021-06-30
actual
84 | construction of a 3 stance pit latrine at Mabonwa catholic Primay School | Rukiiri subcounty | plan | 15,230,000= | GOU | Works | SELECTIVE BIDDING | admeasurement | yes | 2020-08-12 | 2020-08-26 | 2020-09-01 | 2020-09-04 | 2020-09-21 | 2020-09-25 | 30-02-2021
actual
| Prepared by |  |  | Albus Tumwekwatse
Signature:
|  | Position: |  | Senior Procurement Officer
Date:
| Approved by | Name: |  | AHIMBISIBWE NATHAN
Signature:
|  | Position: |  | CHIEF ADMINISTRATIVE OFFICER
Date:

## Consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - FOR SUBMISSION TO THE SECRETARY TO TREASURY, PPDA AND PUBLICATION
Procuring and Disposing Entity:
Financial Year:
S/No | Subject of procurement | Plan vs. Actual | Estimated cost and currency | Source of funding | Procurement method | Contract type | Request for Expression of Interest |  |  |  | Invitation of proposals and approval for award |  |  |  |  | Completion date
[7 empty] | Invitation of Expressions of Interest date | Closing-Opening date | Approval of shortlist | Notification date | Invitation of proposals date | Submission/ opening date | Approval of final evaluation report | Notification date | Contract signing date
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| Prepared by |  | Name: |  |  |  | Approved by | Name
|  |  | Signature: |  |  |  |  | Signature:
|  |  | Designation: |  |  |  |  | Designation:
|  |  | Date: |  |  |  |  | Date:

## Consultancy - Internal use
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - INTERNAL USE
Name of the Procuring Entity:
Financial Year:
S/No. | Subject of Procurement | Plan vs. Actual | Basic Data |  |  |  | Request for Expression of Interest |  |  |  | Preparation of RFP Documents |  | Invitation of proposals and approval for award | [6 empty] | Contract Finalization
|  |  | Estimated Cost and Currency | Procurement Method | Selection Method | Contract Type | Invitation |  | Evaluation |  |  |  | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F)
[7 empty] | Invitation Date | Closing-Opening | Submission Evaluation Report | Approval of Shortlist | Prep & Submission by PDU | Approval by CC | Invitation Date | Submission/ Opening Date | Submission Evaluation Report | Approval of Technical Evaluation Report. | Opening Financial Proposals | Submission of Final Evaluation Report | Approval EvaluationReport | Contract Value | Contract Award Date | Contract Signature Date
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
Plan
Actual
| Total Cost | Plan
Actual
| Prepared by |  | Name:
Signature:
Designation:
Date:
| Approved by |  | Name:
Signature:
Designation:
Date: